## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
My Project | Story 1 | muhammad andka | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
My Project | Story 1 | muhammad andka | 6 | 4 | 2 | 1 | 0 | 0 | 1 | 2 | 3 | 4 | 1
My Project | Story 1 | muhammad andka | 5 | 5 | 3 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 1
My Project | Story 2 | alfonso daniel | 9 | 8 | 2 | 8 | 7 | 3 | 1 | 0 | 2 | 0 | 0
My Project | Story 2 | alfonso daniel | 8 | 2 | 2 | 2 | 2 | 7 | 2 | 0 | 0 | 0 | 2
My Project | Story 2 | alfonso daniel | 9 | 2 | 9 | 9 | 9 | 9 | 3 | 2 | 0 | 0 | 3
My Project | Story 3 | maruli tua napitulu | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 2 | 0 | 0
My Project | Story 3 | maruli tua napitulu | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 1 | 0 | 2 | 1
My Project | Story 3 | maruli tua napitulu | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 1 | 1 | 0 | 1
My Project | Story 4 | muhammad andka | 8 | 3 | 4 | 2 | 8 | 2 | 4 | 1 | 2 | 2 | 1
My Project | Story 4 | muhammad andka | 6 | 4 | 6 | 6 | 6 | 6 | 2 | 1 | 2 |  | 1
My Project | Story 4 | muhammad andka | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 1 | 0 | 2 | 1
My Project | Story 4 | muhammad andka | 9 | 9 | 9 | 9 | 9 | 9 | 4 | 2 | 0 | 0 | 2
Ideal - Remaining efforts in uninterrupted working hours |  |  | 87 | 78.3 | 69.6 | 60.9 | 52.2 | 43.5 | 34.8 | 26.1 | 17.4 | 8.7 | -1.4211e-14
Actual - Remaining efforts in uninterrupted working hours |  |  | 87 | 64 | 59 | 60 | 64 | 59 | 27 | 14 | 13 | 11 | 14
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered